## Contracts
Contract No | Customer Name | Customer Address | Installation Address | Product Days | Installation Days | Load Capacity (kg) | Speed (m/min) | Motor Brand | Motor Power | Control System Brand | Number of Stops | Number of Floors Served | Electrical Box Brand | Pit Depth (mm) | Overhead (mm) | Steel Frame | Shaft Wall Material | Cabin Door Material | Landing Door Material | Start Date | Product End | Installation End | Source File
072 - 26/HĐKT-HTP | NGUYỄN TRỌNG BÌNH | 119/32 Ba Tháng Hai, Phường 11, Quận 10, TP Hồ Chí Minh | 51/24 Cao Thắng, Phường Bàn Cờ, TP HCM | 30 | 30 | 450 | 60 | ZIEHL-ABEGG | 3,1 KW | MITSUBISHI | 6 | 6 | MITSUBISHI | 0 | 0 | NO |  |  |  | 2026-04-14 | 2026-05-14 | 2026-06-13 | C:/Users/admin/Desktop/Capstone/072-26 HĐKT-Ông NGUYỄN TRỌNG BÌNH.pdf
106- 25/HĐKT-HTP | Anh Lân | 51 Hoàng Văn Thụ, Ngọc Trạo, Thanh Hoá | 508/6 Trường Chinh, Tân Bình, TP HCM | 60 | 30 | 450 | 60 | MONTANARI | 3,1 KW | MITSUBISHI | 6 | 6 | MITSUBISHI | 0 | 0 | NO |  |  |  | 2026-04-14 | 2026-06-13 | 2026-07-13 | C:/Users/admin/Desktop/Hợp đồng thang/106-25 HĐKT anh Lân.pdf
118- 25/HĐKT-HTP | MAI THỊ KIM PHƯA | 68 Đinh Công Tráng, Phường Tân Định, Quận 1, TP Hồ Chí Minh | 549/58/72 Điện Biên Phủ, P25, Bình Thạnh, HCM | 30 | 30 | 320 | 60 | FUJI | 3,1 KW | FUJI | 6 | 13 | FUJI | 0 | 0 | NO |  |  |  | 2026-04-14 | 2026-05-14 | 2026-06-13 | C:/Users/admin/Desktop/Hợp đồng thang/118-25 HĐKT- Bà MAI THỊ KIM PHƯA (sales K Hoàng ).pdf

## Tasks
Contract No | Customer Name | Task Type | Start Date | End Date
072 - 26/HĐKT-HTP | NGUYỄN TRỌNG BÌNH | Product | 2026-04-14 | 2026-05-14
072 - 26/HĐKT-HTP | NGUYỄN TRỌNG BÌNH | Installation | 2026-05-14 | 2026-06-13
106- 25/HĐKT-HTP | Anh Lân | Product | 2026-04-14 | 2026-06-13
106- 25/HĐKT-HTP | Anh Lân | Installation | 2026-06-13 | 2026-07-13
118- 25/HĐKT-HTP | MAI THỊ KIM PHƯA | Product | 2026-04-14 | 2026-05-14
118- 25/HĐKT-HTP | MAI THỊ KIM PHƯA | Installation | 2026-05-14 | 2026-06-13